## Title & VLOs
Title and VLO Major Program Modification Process Chart - 2023/2024*
Major Program Modification Process (#OP 2-213B) |  |  | 2023 | [7 empty] | 2024
Stage 1: Modification Confirmation & Initiation |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
1.1 | Program Team includes program modification in Program Improvement Plan (PIP) | Program Coordinator | bar: 2023 MAY to 2023 JUN
1.2 | Program Dean approves PIP | Program Dean | bar: 2023 MAY to 2023 JUN
1.3 | Program Team completes Major Program Change Form and sends to Program Dean | Program Coordinator | bar: 2023 MAY to 2023 JUN
1.4 | Program Dean consults Dean, Academic Quality for direction on whether program change is major or minor | Program Dean | bar: 2023 JUN
1.5 | Dean, Academic Quality confirms modification is major program change requiring external approval | Dean, Academic Quality | bar: 2023 JUN
1.6 | Dean, Academic Quality sends form to PIC for consideration | Dean, Academic Quality | bar: 2023 JUN
1.7 | Associate Vice President (AVP), Academic Experience and AVP, Academic Operations approve curriculum change before resources are assigned to project | AVPAE, AVPAO | bar: 2023 JUN
1.8 | Dean, Academic Quality assigns Program Development Lead (PDL) to lead program modification development team | Dean, Academic Quality | bar: 2023 JUN
1.9 | Program Chair SWFs faculty to complete CVS application with LDST support | Program Chair | bar: 2023 JUN
1.1 | Dean, Academic Quality assigns member of the Learning and Design Support Team (LDST) to program modification team | Dean, Academic Quality | bar: 2023 SEPT
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 2: Program Outline & Briefing Note Development |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
2.1 | PDL reviews NOC code and latest program environmental scan. If environmental scan is > 1 year old, PDL requests environmental scan update by Library Resource Team (LRT) | PDL | bar: 2023 SEPT
2.2 | Manager, Library and Learning Services assigns environmental scan to Library Resource Team (LRT) | Manager, Library and Learning Services | bar: 2023 SEPT
2.3 | LRT completes environmental scan and submits to PDL, PDL then sends to Workforce & Labour Market Advisor (WLMA) | LRT/PDL | bar: 2023 SEPT to 2023 OCT
2.4 | WLMA completes LMI executive summary and sends to PDL , then PDL sends scan and summary to Program Dean | WLMA/PDL | bar: 2023 SEPT to 2023 OCT
2.5 | PDL schedules and leads program modification team meetings if required | PDL | bar: 2023 SEPT to 2023 NOV
| 2.51 - LDST and SME complete CVS application in consultation with program modification team | LDST/SME | bar: 2023 OCT to 2023 NOV
| 2.52 - Program Chair consults with other curriculum providers (GAS, IP) | Program Chair | bar: 2023 OCT to 2023 NOV
| 2.53 - PDL determines if Program Delivery Information (PDI) table must be updated | PDL | bar: 2023 OCT to 2023 NOV
2.6 | Program Dean/Chair presents modification to Academic Council for consultation | Program Dean/Chair | bar: 2023 OCT to 2023 NOV
2.7 | PDL populates draft BoG briefing note with minimum required information and sends to Program Dean for completion | Program Dean/PDL | bar: 2023 OCT to 2023 DEC
2.8 | Program Dean or Coordinator presents modification to Program PAC for formal endorsement | Program Dean/ Coordinator | bar: 2023 NOV to 2023 DEC
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 3: Approvals |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
3.1 | LDST submits CVS application to OCQAS for review | LDST | bar: 2023 NOV to 2023 DEC
3.2 | LDST submits CVS application to OCQAS for validation | LDST | bar: 2023 NOV to 2023 DEC
3.3 | Dean, Academic Quality informs President, AVP, Academic Operations, AVP, Academic Experience and Program Dean of CVS response | Dean, Academic Quality | bar: 2023 NOV to 2023 DEC
3.4 | Program Dean presents briefing note to AVP, Academic Operations and AVP, Academic Experience for approval | Program Dean | bar: 2023 DEC
3.5 | Program Dean presents briefing note to SMT for approval to move to BoG for final College approval | Program Dean | bar: 2023 DEC
3.6 | Program Dean will be informed one month prior to BoG date that the agenda has been confirmed for presentation of program modification | Operations Officer, Office of EVP | bar: 2023 DEC
3.7 | EVP, Academic and Applied Research and Innovation presents briefing note using BoG briefing note template to BoG for final College approval (CVS validation is required before presentation to the BoG) | EVPAARI | bar: 2024 JAN
3.8 | PDL populates PFAAM application and sends application to Dean, Academic Quality for review and President's signature | PDL/Dean, Academic Quality | bar: 2024 JAN
3.9 | PDL submits signed funding application through PFAAM to MCU for final Ministry approval | PDL | bar: 2024 JAN to 2024 FEB
3.10 | Dean, Academic Quality informs AVPAO, AVPAE and Program Dean of MCU response | Dean, Academic Quality | bar: 2024 JAN to 2024 FEB
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 4: Implementation |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
4.1 | Dean, Academic Quality sends memo and MCU approval letter to RO, AO, Finance, Marketing & other departments, and approved major program change form to AO | Dean, Academic Quality | bar: 2024 FEB
4.2 | RO loads changes into OCAS if applicable | RO | bar: 2024 FEB
4.3 | AO loads changes into Evolve if applicable | AO | bar: 2024 FEB
4.4 | Quality Assurance Administrative Assistant updates VLO map if applicable | Quality Assurance Admin Assistant | bar: 2024 FEB to 2024 MAR
4.5 | PDL updates Program Delivery Information in Evolve if applicable | PDL | bar: 2024 FEB to 2024 MAR
4.6 | Program Dean/Chair presents final briefing note to PIC | Program Dean/Chair | bar: 2024 FEB
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 5: Curriculum Development |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
5.1 | Program Chair identifies and SWFs any course development required, and submits project request to LDST for support | Program Chair | bar: 2024 MAR to 2024 APR
5.2 | SMEs develop curriculum and learning design with LDST support | SMEs/LDST | bar: 2024 MAY to 2024 JUNE
5.3 | SMEs submit new course outlines to Program Chair for approval if applicable | SMEs | bar: 2024 MAY to 2024 JUNE
5.4 | SMEs submit any remaining course outlines to AO if applicable, and in accordance with academic timelines | SMEs | bar: 2024 SEPT
5.5 | Annual Program Review Process | Dean, Academic Quality | bar: 2024 SEPT
5.6 | Cyclical Program Review Process | Dean, Academic Quality | bar: 2024 SEPT
*revised August 2023
| Academic Operations Department | AO
| Associate Vice President, Academic Experience | AVPAE
| Associate Vice President, Academic Operations | AVPAO
| Board of Governors | BoG
| Credentials Validation Service | CVS
| Environmental Scan | ES
| Executive Vice President, Academic and Applied Research and Innovation | EVPAARI
| General Arts and Science | GAS
| Indigenous Perspectives | IP
| Learning Design Support Team | LDST
| Library Resource Team | LRT
| Ministry of Colleges & Universities | MCU
| Ontario College Quality Assurance Service | OCQAS
| Program Advisory Committee | PAC
| Program Development Lead | PDL
| Program Funding Approvals and Administration Module (MCU) | PFAAM
| Program Implementation Committee | PIC
| Registrar's Office | RO
| Subject Matter Expert | SME
| Senior Management Team | SMT
| Standard Workload Form | SWF
| Vocational Learning Outcomes | VLO
| Workforce & Labour Market Advisor | WLMA

## Program Delivery
Program Delivery Major Program Modification Process Chart - 2023/2024*
Major Program Modification Process (#OP 2-213B) |  |  | 2023 | [7 empty] | 2024
Stage 1: Modification Confirmation & Initiation |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
1.1 | Program Team includes program modification in Program Improvement Plan (PIP) | Program Coordinator | bar: 2023 MAY to 2023 JUN
1.2 | Program Dean approves PIP | Program Dean | bar: 2023 MAY to 2023 JUN
1.3 | Program Team completes Major Program Change Form and sends to Program Dean | Program Coordinator | bar: 2023 JUN
1.4 | Program Dean consults Dean, Academic Quality for direction on whether program change is major or minor | Program Dean | bar: 2023 JUN
1.5 | Dean, Academic Quality confirms modification is major program change requiring external approval | Dean, Academic Quality | bar: 2023 JUN
1.6 | Dean, Academic Quality sends form to PIC for consideration | Dean, Academic Quality | bar: 2023 JUN
1.7 | Associate Vice President (AVP), Academic Experience and AVP, Academic Operations approve curriculum change before resources are assigned to project | AVPAE, AVPAO | bar: 2023 JUN
1.8 | Dean, Academic Quality assigns Program Development Lead (PDL) to lead program modification development team | Dean, Academic Quality | bar: 2023 JUN
1.9 | Program Chair SWFs faculty if course level curriculum change is anticipated (i.e. change in number of semesters, addition of placement course) | Program Chair | bar: 2023 JUN
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 2: Briefing Note Development |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
2.1 | PDL reviews NOC code and latest program environmental scan. If environmental scan is > 1 year old, PDL requests environmental scan update by Library Resource Team (LRT) | PDL | bar: 2023 SEPT
2.2 | Manager, Library and Learning Services assigns environmental scan to Library Resource Team (LRT) | Manager, Library and Learning Services | bar: 2023 SEPT
2.3 | LRT completes environmental scan and submits to PDL, PDL then sends to Workforce & Labour Market Advisor (WLMA) | LRT/PDL | bar: 2023 SEPT to 2023 OCT
2.4 | WLMA completes LMI executive summary and sends to PDL , then PDL sends scan and summary to Program Dean | WLMA/PDL | bar: 2023 SEPT to 2023 OCT
2.5 | PDL schedules and leads program modification team meetings if applicable | PDL | bar: 2023 SEPT to 2023 OCT
| 2.51 - if course level change is involved (i.e. change in number of semesters, addition of placement course), LDST support is requested to support SME with any curriculum development | Program Chair/ SME/LDST | bar: 2023 SEPT to 2023 OCT
| 2.52 - Program Chair consults with other curriculum providers (GAS, IP) | Program Chair | bar: 2023 SEPT to 2023 OCT
2.6 | Program Dean/Chair presents modification to Academic Council for consultation | Program Dean/Chair | bar: 2023 OCT to 2023 NOV
2.7 | PDL populates draft BoG briefing note with minimum required information and sends to Program Dean for completion | Program Dean/PDL | bar: 2023 OCT to 2023 NOV
2.8 | Program Dean or Coordinator presents modification to Program PAC for formal endorsement | Program Dean/ Coordinator | bar: 2023 NOV to 2023 DEC
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 3: Approvals |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
3.1 | Program Dean presents briefing note to AVPAO and AVPAE for approval | Program Dean | bar: 2023 NOV to 2023 DEC
3.2 | Program Dean presents briefing note to SMT for approval to move to BoG for College approval | Program Dean | bar: 2023 NOV to 2023 DEC
3.3 | Program Dean will be informed one month prior to BoG date that the agenda has been confirmed for presentation of program modification | Operations Officer, Office of EVP | bar: 2023 DEC
3.4 | EVP, Academic and Applied Research and Innovation presents briefing note using BoG briefing note template to BoG for College approval | EVPAARI | bar: 2024 JAN
3.5 | PDL populates PFAAM application and sends application to Dean, Academic Quality for review and President's signature | PDL/Dean, Academic Quality | bar: 2024 JAN
3.6 | PDL submits signed funding application through PFAAM to MCU for final Ministry approval | PDL | bar: 2024 JAN
3.7 | Dean, Academic Quality informs AVPAO, AVPAE and Program Dean of MCU response | Dean, Academic Quality | bar: 2024 JAN to 2024 FEB
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 4: Implementation |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
4.1 | Dean, Academic Quality sends memo and MCU approval letter to RO, AO, Finance, Marketing & other departments, and approved major program change form to AO | Dean, Academic Quality | bar: 2024 FEB
4.2 | RO loads changes into OCAS if applicable | RO | bar: 2024 FEB
4.3 | AO loads changes into Evolve if applicable | AO | bar: 2024 FEB
4.4 | PDL updates Program Delivery Information in Evolve | PDL | bar: 2024 FEB
4.5 | Program Dean/Chair presents final briefing note to PIC | Program Dean/Chair | bar: 2024 FEB
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 5: Curriculum Development |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
5.1 | Program Chair identifies and SWFs any course development required, and submits project request to LDST for support | Program Chair | bar: 2024 MAR to 2024 APR
5.2 | SMEs develop curriculum and learning design with LDST support | SMEs/LDST | bar: 2024 MAY to 2024 JUNE
5.3 | SMEs submit new course outlines to Program Chair for approval if course change involved | SMEs | bar: 2024 MAY to 2024 JUNE
5.4 | SMEs submit any remaining course outlines to AO if applicable, and in accordance with academic timelines | SMEs | bar: 2024 SEPT
5.5 | Annual Program Review Process | Dean, Academic Quality | bar: 2024 SEPT
5.6 | Cyclical Program Review Process | Dean, Academic Quality | bar: 2024 SEPT
*revised August 2023
| Academic Operations Department | AO
| Associate Vice President, Academic Experience | AVPAE
| Associate Vice President Academic Operations | AVPAO
| Board of Governors | BoG
| Credentials Validation Service | CVS
| Environmental Scan | ES
| Executive Vice President, Academic and Applied Research and Innovation | EVPAARI
| General Arts and Science | GAS
| Indigenous Perspectives | IP
| Learning Design Support Team | LDST
| Library Resource Team | LRT
| Ministry of Colleges & Universities | MCU
| Ontario College Quality Assurance Service | OCQAS
| Program Advisory Committee | PAC
| Program Development Lead | PDL
| Program Funding Approvals and Administration Module (MCU) | PFAAM
| Program Implementation Committee | PIC
| Registrar's Office | RO
| Subject Matter Expert | SME
| Senior Management Team | SMT
| Standard Workload Form | SWF
| Vocational Learning Outcomes | VLO
| Workforce & Labour Market Advisor | WLMA

## Admission Requirements
Admission Requirements Major Program Modification Process Chart - 2023/2024*
Major Program Modification Process (#OP 2-213B) |  |  | 2023 | [7 empty] | 2024
Stage 1: Modification Confirmation & Initiation |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
1.1 | Program Team includes program modification in Program Improvement Plan (PIP) | Program Coordinator | bar: 2023 MAY to 2023 JUN
1.2 | Program Dean approves PIP | Program Dean | bar: 2023 MAY to 2023 JUN
1.3 | Program Team completes Major Program Change Form and sends to Program Dean | Program Coordinator | bar: 2023 JUN
1.4 | Program Dean consults Dean, Academic Quality for direction on whether program change is major or minor | Program Dean | bar: 2023 JUN
1.5 | Dean, Academic Quality confirms modification is major program change requiring external approval | Dean, Academic Quality | bar: 2023 JUN
1.6 | Dean, Academic Quality sends major change form to PIC for consideration | Dean, Academic Quality | bar: 2023 JUN
1.7 | Associate Vice President (AVP), Academic Experience and AVP, Academic Operations approve curriculum change before resources are assigned to project | AVPAE, AVPAO | bar: 2023 JUN
1.8 | Dean, Academic Quality assigns Program Development Lead (PDL) to lead program modification development team | Dean, Academic Quality | bar: 2023 SEPT
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 2: Briefing Note Development |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
2.1 | PDL reviews NOC code and latest program environmental scan. If environmental scan is > 1 year old, PDL requests environmental scan update by Library Resource Team (LRT) | PDL | bar: 2023 SEPT
2.2 | Manager, Library and Learning Services assigns environmental scan to Library Resource Team (LRT) | Manager, Library and Learning Services | bar: 2023 SEPT
2.3 | LRT completes environmental scan and submits to PDL, PDL then sends to Workforce & Labour Market Advisor (WLMA) | LRT/PDL | bar: 2023 SEPT to 2023 OCT
2.4 | WLMA completes LMI executive summary and sends to PDL , then PDL sends scan and summary to Program Dean | WLMA/PDL | bar: 2023 SEPT to 2023 OCT
2.5 | PDL schedules and leads program modification team meetings if required | Program Dean/PDL | bar: 2023 SEPT to 2023 OCT
2.6 | Program Dean/Chair presents modification to Academic Council for consultation | Program Dean/Chair | bar: 2023 OCT to 2023 NOV
2.7 | PDL populates draft BoG briefing note with minimum required information and sends to Program Dean for completion | Program Dean/PDL | bar: 2023 OCT to 2023 NOV
2.8 | Program Dean or Coordinator presents modification to Program PAC for formal endorsement | Program Dean/ Coordinator | bar: 2023 OCT to 2023 NOV
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 3: Approvals |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
3.1 | Program Dean presents briefing note to AVPAO and AVPAE for approval | Program Dean | bar: 2023 OCT to 2023 NOV
3.2 | Program Dean presents briefing note to SMT for approval to move to BoG for final College approval | Program Dean | bar: 2023 OCT to 2023 NOV
3.3 | Program Dean will be informed one month prior to BoG date that the agenda has been confirmed for presentation of program modification | Operations Officer, Office of EVP | bar: 2023 OCT to 2023 NOV
3.4 | EVP, Academic and Applied Research and Innovation presents briefing note using BoG briefing note template to BoG for final college approval | EVPAARI | bar: 2023 NOV
3.5 | PDL drafts letter to CVS and sends to Dean, Academic Quality for completion | PDL | bar: 2023 NOV
3.6 | Dean, Academic Quality submits letter to CVS for approval (if approved, CVS sends approval to MCU) | Dean, Academic Quality | bar: 2023 NOV to 2023 DEC
3.7 | Dean, Academic Quality informs President, AVPAE, AVPAO and Program Dean of CVS response | Dean, Academic Quality | bar: 2023 NOV to 2023 DEC
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage 4: Implementation |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
4.1 | Dean, Academic Quality sends memo to RO, AO, Finance, Marketing & other departments, and approved major program change form to AO | Dean, Academic Quality | bar: 2023 DEC to 2024 JAN
4.2 | RO loads changes into OCAS | RO | bar: 2023 DEC to 2024 JAN
4.3 | AO loads changes into Evolve | AO | bar: 2023 DEC to 2024 JAN
4.4 | Program Dean/Chair presents final briefing note to PIC | Program Dean/Chair | bar: 2024 JAN to 2024 FEB
*revised August 2023
| Academic Operations Department | AO
| Associate Vice President, Academic Experience | AVPAE
| Associate Vice President Academic Operations | AVPAO
| Board of Governors | BoG
| Credentials Validation Service | CVS
| Environmental Scan | ES
| Executive Vice President, Academic and Applied Research and Innovation | EVPAARI
| General Arts and Science | GAS
| Indigenous Perspectives | IP
| Learning Design Support Team | LDST
| Library Resource Team | LRT
| Ministry of Colleges & Universities | MCU
| Ontario College Quality Assurance Service | OCQAS
| Program Advisory Committee | PAC
| Program Development Lead | PDL
| Program Funding Approvals and Administration Module (MCU) | PFAAM
| Program Implementation Committee | PIC
| Registrar's Office | RO
| Subject Matter Expert | SME
| Senior Management Team | SMT
| Standard Workload Form | SWF
| Vocational Learning Outcomes | VLO
| Workforce & Labour Market Advisor | WLMA

## Delivery Method
Delivery Method Major Program Modification Process Chart - 2023/2024*
Major Program Modification Process (#OP 2-213B) |  |  | 2023 | [7 empty] | 2024
Stage I: Modification Consultation and Approval |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
1.1 | Program Team includes program modification in Program Improvement Plan (PIP) | Program Coordinator | bar: 2023 MAY to 2023 JUN
1.2 | Program Dean approves PIP | Program Dean | bar: 2023 MAY to 2023 JUN
1.3 | Program Team completes Major Program Change Form and sends to Program Dean | Program Coordinator | bar: 2023 JUN
1.4 | Program Dean consults Dean, Academic Quality for direction on whether program change is major or minor | Program Dean | bar: 2023 JUN
1.5 | Dean, Academic Quality sends form to PIC for consideration (major change form sent to AO for information) | Dean, Academic Quality | bar: 2023 JUN
1.6 | Associate Vice President (AVP), Academic Experience and AVP, Academic Operations approve curriculum change before resources are assigned to project | AVPAE, AVPAO | bar: 2023 JUN
1.7 | Program Dean/Chair presents modification to Academic Council for consultation | Program Dean/Chair | bar: 2023 SEPT to 2023 OCT
1.8 | Program Dean or Coordinator presents modification to Program PAC for formal endorsement | Program Dean/ Coordinator | bar: 2023 OCT
1.9 | Program Coordinator populates and sends Curriculum Change Approval forms to Program Dean/Chair for approval, and then sends to AO | Program Coordinator/ Program Dean/Chair | bar: 2023 OCT to 2023 NOV
1.1 | AO loads curriculum changes into Evolve | AO | bar: 2023 OCT to 2023 NOV
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage II: Curriculum Development |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
2.1 | Program Chair identifies and SWFs any course development required, and submits project request with LDST for support | Program Chair | bar: 2023 NOV to 2023 DEC
2.2 | SMEs develop curriculum and learning design with LDST support | SMEs/LDST | bar: 2024 JAN to 2024 JUNE
2.3 | Program Chair consults with other curriculum providers (GAS, IP) | Program Chair | bar: 2024 JAN to 2024 JUNE
2.4 | SMEs submit new course outlines to Program Chair for approval | SMEs | bar: 2024 MAY to 2024 JUNE
2.5 | SMEs submit any remaining course outlines to AO if applicable, and in accordance with academic timelines | SMEs | bar: 2024 SEPT
2.6 | Annual Program Review Process | Dean, Academic Quality | bar: 2024 SEPT
2.7 | Cyclical Program Review Process | Dean, Academic Quality | bar: 2024 SEPT
*revised August 2023
| Academic Operations Department | AO
| Associate Vice President, Academic Experience | AVPAE
| Associate Vice President Academic Operations | AVPAO
| Board of Governors | BoG
| Credentials Validation Service | CVS
| Curriculum Change Approval forms | CCA
| Environmental Scan | ES
| Executive Vice President, Academic and Applied Research and Innovation | EVPAARI
| General Arts and Science | GAS
| Indigenous Perspectives | IP
| Learning Design Support Team | LDST
| Library Resource Team | LRT
| Ministry of Colleges & Universities | MCU
| Ontario College Quality Assurance Service | OCQAS
| Program Advisory Committee | PAC
| Program Development Lead | PDL
| Program Funding Approvals and Administration Module (MCU) | PFAAM
| Program Implementation Committee | PIC
| Registrar's Office | RO
| Subject Matter Expert | SME
| Senior Management Team | SMT
| Standard Workload Form | SWF
| Vocational Learning Outcomes | VLO
| Workforce & Labour Market Advisor | WLMA

## WIL
Work Integrated Learning (WIL) Major Program Modification Process Chart - 2023/2024*
Major Program Modification Process (#OP 2-213B) |  |  | 2023 | [7 empty] | 2024
Stage I: Modification Consultation and Approval |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
1.1 | Program Team includes program modification in Program Improvement Plan (PIP) | Program Team | bar: 2023 MAY to 2023 JUN
1.2 | Program Dean approves PIP | Program Dean | bar: 2023 MAY to 2023 JUN
1.3 | Program Team completes Major Program Change Form and sends to Program Dean | Program Team | bar: 2023 JUN
1.4 | Program Dean consults Dean, Academic Quality for direction on whether program change is major or minor | Program Dean | bar: 2023 JUN
1.5 | Program Development Lead will review PDI to ensure Program Delivery change does not require MCU approval (e.g., addition/removal of co-op) and notify Dean, Academic Quality | PDL | bar: 2023 JUN
1.6 | Dean, Academic Quality confirms whether change is major | Dean, Academic Quality | bar: 2023 JUN
1.7 | Dean, Academic Quality sends form to PIC for consideration (major change form sent to AO for information) | Dean, Academic Quality | bar: 2023 JUN
1.8 | Associate Vice President (AVP), Academic Experience and AVP, Academic Operations approve curriculum change before resources are assigned to project | AVPAE, AVPAO | bar: 2023 JUN
1.9 | Program Dean/Chair presents modification to Academic Council for consultation | Program Dean/Chair | bar: 2023 SEPT to 2023 OCT
1.1 | Program Dean or Coordinator presents modification to Program PAC for formal endorsement | Program Dean/ Coordinator | bar: 2023 OCT
1.11 | Program Coordinator populates and sends Curriculum Change Approval forms to Program Dean/Chair for approval, and then sends to AO | Program Coordinator/ Program Dean/Chair | bar: 2023 OCT to 2023 NOV
1.12 | AO loads curriculum changes into Evolve | AO | bar: 2023 OCT to 2023 NOV
Major Program Modification Process (#OP 2-213B) |  |  | 2023 MAY: 2023; 2024 JAN: 2024
Stage II: Curriculum Development |  | LEAD | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
2.1 | Program Chair identifies and SWFs any course development required, and submits project request to LDST for support | Program Chair | bar: 2023 NOV to 2023 DEC
2.2 | SMEs develop curriculum and learning design with LDST support | SMEs/LDST | bar: 2024 JAN to 2024 JUNE
2.3 | Program Chair consults with other curriculum providers (GAS, IP) | Program Chair | bar: 2024 JAN to 2024 JUNE
2.4 | SMEs submit new course outlines to Program Chair for approval | SMEs | bar: 2024 MAY to 2024 JUNE
2.5 | SMEs submit any remaining course outlines to AO if applicable, and in accordance with academic timelines | SMEs | bar: 2024 SEPT
2.6 | Annual Program Review Process | Dean, Academic Quality | bar: 2024 SEPT
2.7 | Cyclical Program Review Process | Dean, Academic Quality | bar: 2024 SEPT
*revised August 2023
| Academic Operations Department | AO
| Associate Vice President, Academic Experience | AVPAE
| Associate Vice President Academic Operations | AVPAO
| Board of Governors | BoG
| Credentials Validation Service | CVS
| Curriculum Change Approval forms | CCA
| Environmental Scan | ES
| Executive Vice President, Academic and Applied Research and Innovation | EVPAARI
| General Arts and Science | GAS
| Indigenous Perspectives | IP
| Learning Design Support Team | LDST
| Library Resource Team | LRT
| Ministry of Colleges & Universities | MCU
| Ontario College Quality Assurance Service | OCQAS
| Program Advisory Committee | PAC
| Program Development Lead | PDL
| Program Funding Approvals and Administration Module (MCU) | PFAAM
| Program Implementation Committee | PIC
| Registrar's Office | RO
| Subject Matter Expert | SME
| Senior Management Team | SMT
| Standard Workload Form | SWF
| Vocational Learning Outcomes | VLO
| Workforce & Labour Market Advisor | WLMA