## Sheet1
New Program Development Process Chart - 2020/2021 (acronym legend located at the bottom of the document)
New Program Development Process* |  | 2020 |  |  |  | 2021 | [11 empty] | 2022
Stage 1: Concept Proposal | LEAD | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
The Program Development Lead is the Project Manager for all stages except Stage 6 where the Teaching & Learning Specialist is the Project Lead.
1.1 Present Concept Proposal (CP) for new program idea to Dean using the Concept Proposal template | idea creator | bar: 2020 OCT
1.2 Present Concept Proposal (CP) for new idea to VPAE & Director, Strategic Planning | Dean | bar: 2020 OCT to 2020 NOV
1.3 Present new program idea to SMT for approval to move onto Stage 2 using SMT briefing note template | Dean | bar: 2020 NOV
1.4 Present new idea to SEM for consultation using SMT briefing note template | Dean | bar: 2020 NOV
1.5 Present new idea to BoG for initial consultation using BoG briefing note template (last Wednesday in month) | VPAE | bar: 2020 NOV to 2020 DEC
1.6 School will be informed 1 month prior to BoG date that the agenda has been confirmed for presentation of new program idea initial check-in | Operations Officer, Office of VPAE | bar: 2020 NOV
1.7 Identification of Program Development Lead (PDL) to assist with process | DSP | bar: 2020 NOV
New Program Development Process |  | 2020 SEPT: 2020; 2021 JAN: 2021; 2022 JAN: 2022
Stage 2: Environmental Scan and Program Scoping | LEAD | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
2.1 Submit CP to Library Research Team (LRT) to generate program environmental scan | DSP/PDL | bar: 2020 OCT
2.2 Manager, Career & Academic Success Services to assign environmental scan to Library Resource Team | Manager, Career & Academic Success Services | bar: 2020 OCT
2.3 LRT completes environmental scan and submits to DSP/PDL and appropriate Dean/Chair | LRT | bar: 2020 NOV to 2020 DEC
2.4 Business Intelligence: LMI to be completed and Executive Summary written | WLMA | bar: 2020 NOV to 2020 DEC
2.5 Confirmation of program idea | Dean | bar: 2020 NOV to 2020 DEC
New Program Development Process |  | 2020 SEPT: 2020; 2021 JAN: 2021; 2022 JAN: 2022
Stage 3: Program Outline & Business Case | LEAD | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
3.1 Identify subject matter expert & assign hours in their workload | Dean/Chair | bar: 2020 NOV to 2021 JAN
3.2 Identify Teaching & Learning Specialist | Dean, Health & Wellness | bar: 2020 NOV to 2021 JAN
3.3 PROGRAM TEAM KICK-OFF MEETING: with in-service | PDL | bar: 2020 NOV
3.4 Creation and engagement of reference group (industry experts) | Dean | bar: 2020 NOV to 2020 DEC
3.5 Engage reference group and program development team | Dean | bar: 2020 NOV to 2021 JAN
3.6 Consult with other curriculum providers | Chair/PDL | bar: 2020 DEC to 2021 JAN
3.7 Develop proposed program outline with VLO's, courses & mapping | TLS | bar: 2020 DEC to 2021 JAN
3.8 Present new program idea to Academic Council for consultation | Dean/Chair | bar: 2020 NOV
3.9 Creation of Business Case using Business Case template | Dean/PDL | bar: 2020 DEC to 2021 JAN
3.10 Develop preliminary program costing in consultation with finance | Dean | bar: 2020 DEC to 2021 JAN
3.11 Present program outline and map to Program Implementation Committee - provide draft Business Case | Dean | bar: 2021 JAN
3.12 Present program outline & concept to reference group for formal endorsement - support letters required | Dean/Chair | bar: 2021 FEB to 2021 MAR
New Program Development Process |  | 2020 SEPT: 2020; 2021 JAN: 2021; 2022 JAN: 2022
Stage 4: Approval Process | LEAD | TLS | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
4.1 CVS application population and submission for review | TLS | bar: 2021 FEB
4.2 Submit CVS application to OCQAS | DSP/TLS | bar: 2021 MAR
4.3 Await CVS approval - inform President, VPAE, Schools of status | DSP
4.4 Present Business Case to Program Implementation Committee (RO, Marketing, Student Services, IT, AO, Chair from GAS) | Dean/Chair | bar: 2021 MAR to 2021 APR
4.5 Business Case to Dean and Director, Strategic Planning | PDL | bar: 2021 MAR
4.6 Present Business Case to VPAE for final approval | Dean/Chair | bar: 2021 MAR
4.7 Present Business Case to President/SMT prior to BoG meeting | VPAE/Dean | bar: 2021 MAR
4.8 Present Business Case to BoG for final approval | VPAE/Dean | bar: 2021 MAR to 2021 MAY
4.9 School will be informed 1 month prior to BoG date that the agenda has been confirmed for presentation of business case | Operations Officer, Office of VPAE | bar: 2021 MAR to 2021 MAY
4.10 Populate MCU funding website and submit funding application to President for signature | DSP/PDL | bar: 2021 APR to 2021 MAY
4.11 Submit funding application to MCU | DSP/PDL | bar: 2021 APR to 2021 MAY
4.12 Await MCU Funding Approval. Inform President, VPAE, Schools of status | DSP/PDL
New Program Development Process |  | 2020 | 2021 JAN: 2021; 2022 JAN: 2022
Stage 5: Operational Implementation | LEAD | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
5.1 Submit program outline to Marketing & other related student service areas | PDL | bar: 2021 MAY
5.2 Program loaded into OCAS | RO | bar: 2021 JUNE
5.3 Program loaded into Evolve | AO | bar: 2021 JUNE
New Program Development Process |  | 2020 SEPT: 2020; 2021 JAN: 2021; 2022 JAN: 2022
Stage 6: Program Launch TLS is the Project Lead in this stage | LEAD | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUNE | JULY | AUG | SEPT
6.1 Identify & SWF curriculum development team (SME) | Chair | bar: 2021 MAR to 2021 APR
6.2 Form curriculum development team | Chair | bar: 2021 MAR to 2021 APR
6.3 Identify Learning Technologist | Dean, Health & Wellness | bar: 2021 MAR
6.4 Facilitate development curriculum & learning design | TLS | bar: 2021 MAY to 2022 JUNE
6.5 Submit SEM 1 course outlines to Chair for approval | Coordinator/Faculty | bar: 2021 MAY to 2022 APR
6.6 Launch Program | bar: 2020 SEPT to 2022 SEPT
6.7 Submit remaining course outlines to AO in accordance with academic timelines | Chair/ Coordinator
6.8 Annual Curriculum Review Process | Dean, Health & Wellness
6.9 Program Review | Dean, Health & Wellness
*updated Nov. 2020
Board of Governors | BoG
Credentials Validation Service | CVS
Director of Strategic Planning | DSP
Essential Employability Skills | EES
Environmental Scan | ES
Library Resource Team | LRT
Ministry of Colleges & Universities | MCU
Ontario College Quality Assurance Service | OCQAS
Program Advisory Committee | PAC
Program Development Lead | PDL
Strategic Enrolment Management | SEM
Strategic Mandate Agreement | SMA
Subject Matter Expert | SME
Senior Management Team | SMT
Standard Workload Form | SWF
Teaching & Learning Specialist | TLS
Vocational Learning Outcomes | VLO
Vice President Academic Experience | VPAE
Workforce & Labour Market Advisor | WLMA