Program: ECE: Coordinators Heather Kay & Mary Lou Lummis Date Fall 2007 continuing through to June 2008

Curriculum Renewal: Analysis and Action Plan Template B. Curriculum Strengths and Challenges Having reflected on the indicators shown above, record the overall curriculum strengths and challenges identified by the team, and include rationale where appropriate.

- Need to focus on children’s health & impact of the environment on it - Need to focus on child guidance principles - Need to evaluate placement of block practicum so students can practice at full scope - Need to define our curriculum philosophy, ensuring it meets current best-practices and then is incorporated through-out our curriculum & practice

C. Action Plan Identify priority action accompanied by rationale plan for upcoming year, indicate who will be responsible, and specify timelines for activities.

- Revise Child Development 1 & 2 to reflect the specific needs of the ECE student –done All, May 2008 - Update course outlines for field practice 3rd semester- done ML, HK, June 2008 - Ensure learning outcomes match the delivery of the weekly course plans-ongoing All Fall 2008 - Re-evaluate gen ed; mandatory vs required- (removed Lifestyle & Wellness & Social Psych as mandatory) Done All June 2008 - Field placement realignment and repositioning Done All May 2008 - Review outcomes for entire program to complete work indicated in Curriculum Renewal 2006- including focus on child guidance & best practice curriculum, connecting theory to practice, play-based learning & pedagogical practice that prepares children to move seamlessly into primary education: 3 courses to be completed this fall include: Child Care Curriculum 1 EDUC4 , Observing Young Children (former EDUC9) & Guiding Young Children’s Behaviors (former EDUC22) Started Jan – June 2008- All Completed by Fall 2008 - Incorporate updated philosophy into each course that aligns with College of ECE & new best practices, ensuring we are teaching what we support- Fall 2008 - Review alignment of placement with theory courses Ongoing ALL - Work with agencies to help them understand our current curriculum & the changing purpose of placement practice (testing their theoretical knowledge as it can enhance child learning) Ongoing ALL - Support current Frost students in their completion of their program & various options for delivery Fall 2008 - Explore part-time offering in collaboration with Con Ed, plus alternate delivery for Frost applicants. June 2008 on - Examine Second Career Options for those interested in ECE

D. Deferred Actions Record long-term plans or issues that will need to be monitored, researched, or deferred for future action.

- Consider Aboriginal Emphasis Option as a value add- work continues May 2008 on - Determine gen ed credit options in our program in collaboration with IDS - Revise evaluation form for placement Fall 2008 start