## Instructions
Purpose of Benefit Register
The purpose of a program or project is to deliver change in an organized, planned structure. For change to be effective, benefit(s) must be identified, managed, and realized for the deliverable(s) and change(s) to be justified and accepted. The benefit register is an up to date list of planned benefits, who is responsible for measuring them, when they are expected to be realized, how they will be measured, baseline and current measurements, et cetera. The benefits in the register should encompass the reason for doing the program/project and justify the time and expense of making the change. Realization of the benefits listed in the register form a critical aspect of measuring program/project success.
Benefit Register Participants and Audience
Input into the benefit register may come from many different sources including, but not limited to, Sponsor, senior leadership, program/project intake form and/or business case, organizational and/or business unit strategic plans and initiatives, existing documentation, subject matter experts within business unit(s), and other stakeholders (such as staff, students, faculty).
The author and maintainer is the Program/Project Manager. Changes to benefits should be authorized through a formal Change Request by the Sponsor.
Instructions
1. Research and understand program/project information by reading any prior documentation (such as intake form(s), business case(s), and research/analysis) and speaking to Sponsor and other stakeholders. Identify why the program/project is being approved, what the expectations are for the final results, and what would make the deliverable(s) successful in the eyes of the sponsor and other stakeholders. These types of questions will help identify the benefits, which will sometimes be tied to business strategies/goals/objectives. Benefits, whether tangible or intangible, must be measurable.
2. Enter benefits in the benefit register with input from applicable stakeholders and Sponsor by filling out the applicable sections in the spreadsheet. The green italic text provides an example of a benefit and may be removed. See the Definitions page for a further description of each column on the spreadsheet, as well as valid values.
3. Update the document, as required, to reflect approved benefit changes as the program/project evolves.
4. Execute benefit measurements as outlined in register, recording actual results appropriately.
5. Upload to the Knowledge Base
Next Steps
Execute and document the benefit measurements according to the information laid out in this document. Update this document to reflect any approved changes during program/project execution. Monitor this register throughout execution to ensure that the program/project remains on track to deliver the expected benefits. Reflect final measurements in this document at the end of the program/project and use this document during program/project closure to assess program success.

## Benefits Register
Benefit ID | Benefit Title and Description | Requestor | State | Link to Objectives (Project, Business, Strategic) | Owner | Planned Outcome | Stakeholders and Beneficiaries | Program/Project ID and/or Name | Measure Description & Expected Result | Baseline Measure | Measure Frequency | Actual Measures | Status | Expected Realization Date | Actual Realization Date
e.g. BEN-001 | Reduce the time for managers to fill vacant positions | Leaders Forum | Active | Improve processes and strengthen relations with clients | Joe Blow | The process for approving, posting and recruiting for open positions will be streamlined, reducing the amount of time it takes to fill a vacant position, ensuring continuous University services during employee turnover | Hiring Managers, departments and employees on campus using services impacted by employee turnover, applicants, recruiters | Recruitment System Implementation | Measurement: average # of days across all vacant positions from employee's last day of work to the first day the new employee starts work; Expected Result: less than one month | Baseline measurement before new system implementation is an average of 3 months | 6 months after go live; semi annually after that to assess trending | Jan 15, 1991: 2 months | On Track | 1992-01-01 | 1992-09-01
Note on A1: Salonen, Deb: Sequential numbering in the format BEN-###.
Note on B1: Salonen, Deb: A description of the desired benefit, including a title, current and target state/measurement
Note on C1: Salonen, Deb: The individual that raised the benefit for inclusion as part of the Program.
Note on D1: Salonen, Deb: hat state is the benefit o Active o Future
Note on E1: Salonen, Deb: Document which University or IT Strategy/Strategies this benefit aligns to, and how
Note on F1: Salonen, Deb: The individual responsible for measuring benefit progress, and accomplishing the benefit objective.
Note on G1: Salonen, Deb: What changes will take place, and what will the results look like, in order to achieve the benefit (“Benefit Vision”)
Note on H1: Salonen, Deb: Individuals or groups who will be impacted by and/or benefit from the Planned Outcome.
Note on I1: Salonen, Deb: The ID (from the Portfolio list) and name of the project(s) or initiative(s) within the Program that will deliver the Planned Outcome.
Note on J1: Salonen, Deb: What measurement will be used to gauge progress and success in achieving the benefit? What value is required to be deemed a success?
Note on K1: Salonen, Deb: What was the value of the measure before work started?
Note on L1: Salonen, Deb: How often will a progress measurement take place?
Note on M1: Salonen, Deb: What was the latest progress measurement?
Note on N1: Salonen, Deb: High level status of the progress achieved to date, based on progress measurement versus elapsed time, to deliver the Planned Outcome. o On Track = On Schedule, Budget and Scope o Warning = Significant risk to Schedule, Budget and/or Scope o Critical = Schedule, Budget and/or Scope will not be met o Realized = Benefit realized o NOT Realized = Decision made that benefit will not be realized

## Definitions & Values
Benefit Register Definitions and Values
Benefit ID – A unique identifer or number for each benefit entered | Measure Description & Expected Result – What measurement will be used to gauge progress and success in achieving the benefit? What value is required to be deemed a success?
Benefit Title and Description – A title and brief description of the desired benefit | Baseline Measure – What was the value of the measure before work started?
Requestor – The individual or stakeholder group that raised the benefit for inclusion. | Measure Frequency – How often will a progress measurement take place?
State - State of current benefit. o Active = Benefit is currently active o Future = Benefit is identified for the future | Actual Measures – What are the actual measurement results and the date taken?
Link to Business Objectives – Document or link to University, departmental, or IT strategies this benefit aligns to, and how | Status – High level status of the progress achieved to date, based on progress measurement versus elapsed time, to deliver the Planned Outcome. o Realized = Benefit has been realized. Actual result matches expected. o On Track = On Schedule for realizing benefit. o Warning = Some risk towards realizing benefit. o Critical = Benefit realization will not be met.
Owner – The individual responsible for measuring benefit progress, and accomplishing the benefit objective. | Expected Realization Date – Year and month originally planned for completion of Planned Outcome.
Planned Outcome – What changes will take place, and what will the results look like, in order to achieve the benefit (“Benefit Vision”) | Actual Realization Date – Date of completion of the Planned Outcome/Benefit. If the full benefit is no longer expected, enter N/A
Stakeholders and Beneficiaries – Individuals or groups who will be impacted by and/or benefit from the Planned Outcome.
Program/Project ID and Name – The ID and/or name of the program, project(s), or initiative(s) that will deliver the Planned Outcome

## Sheet1 (hidden)
Active
Future
Realized
On Track
Warning
Critical